## Gantt Chart Template
| PROJECT TITLE | DOA Estimation with Antenna Arrays |  |  | COMPANY NAME
| PROJECT MANAGER |  |  |  | DATE | [10 empty] | 2017-01-18
|  |  |  | Fall Quarter | [69 empty] | Fall Finals | [6 empty] | Winter Break | [21 empty] | Winter Quarter
WBS NUMBER | TASK TITLE | TASK OWNER | PCT OF TASK COMPLETE | WEEK 1 (10/2) | [6 empty] | WEEK 2 (10/9) | [6 empty] | WEEK 3 (10/16) | [6 empty] | WEEK 4 (1023) | [6 empty] | WEEK 5 (10/30) | [6 empty] | WEEK 6 (11/6) | [6 empty] | WEEK 7 (11/13) | [6 empty] | WEEK 8 (11/20) | [6 empty] | WEEK 9 (11/27) | [6 empty] | WEEK 10 (12/4) | [6 empty] | Hiatus (12/11) | [6 empty] | WEEK 1 (12/18 | [6 empty] | WEEK 2 (12/25) | [6 empty] | WEEK 3 (1/1) | [6 empty] | WEEK 1 (1/8) | [6 empty] | WEEK 2 (1/15) | [6 empty] | WEEK 3 (1/22) | [6 empty] | WEEK 4 (1/29) | [6 empty] | WEEK 5 (2/5) | [6 empty] | WEEK 6 (2/12) | [6 empty] | WEEK 7 (2/19) | [6 empty] | WEEK 8 (2/26) | [6 empty] | WEEK 9 (3/5) | [6 empty] | WEEK 10 (3/12)
|  |  |  | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | T | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S
1 | MATLAB Simulation
1.1 | Develop General Phase Delay to Reception Angle Algorithm | Albert | 100% | bar: WEEK 3 (10/16) S to WEEK 7 (11/13) S; WEEK 8 (11/20) S; WEEK 3 (1/22) R to WEEK 3 (1/22) S
1.2 | Model Antenna Parameters | Albert | 100% | bar: WEEK 4 (1023) S to WEEK 5 (10/30) M; WEEK 8 (11/20) S; WEEK 3 (1/22) R to WEEK 3 (1/22) S
1.2.1 | Antenna Electric Length | Matt | 100% | bar: WEEK 4 (1023) S to WEEK 4 (1023) T; WEEK 8 (11/20) S; WEEK 3 (1/22) R to WEEK 3 (1/22) S
1.2.2 | Antenna Number of Elements | Matt | 100% | bar: WEEK 4 (1023) W to WEEK 4 (1023) F; WEEK 8 (11/20) S; WEEK 3 (1/22) R to WEEK 3 (1/22) S
1.2.3 | Antenna Array Spacing | Albert | 100% | bar: WEEK 4 (1023) S to WEEK 5 (10/30) M; WEEK 8 (11/20) S; WEEK 3 (1/22) R to WEEK 3 (1/22) S
1.4 | Simulate Response of Antenna Array to Signals | Albert | 100% | bar: WEEK 5 (10/30) F to WEEK 9 (11/27) M; WEEK 3 (1/22) R to WEEK 3 (1/22) S
2 | LabVIEW Communication | bar: WEEK 1 (10/2) S to WEEK 10 (12/4) S; WEEK 1 (12/18 S to WEEK 8 (2/26) S
2.2 | Port Phase Delay to Reception Angle Algorithm to LabVIEW | Albert | 100% | bar: WEEK 8 (11/20) R to WEEK 8 (11/20) S; WEEK 1 (12/18 S to WEEK 3 (1/1) S; WEEK 3 (1/22) R to WEEK 3 (1/22) S
2.3 | Develop MIMO Synchronization Algorithm | Matt | 30% | bar: WEEK 8 (11/20) S; WEEK 1 (1/8) S to WEEK 2 (1/15) S; WEEK 3 (1/22) R to WEEK 3 (1/22) S
2.4 | Implement Beamforming as a secondary mode of localization | Matt | 0% | bar: WEEK 8 (11/20) S; WEEK 3 (1/22) R to WEEK 5 (2/5) S
2.5 | Calibrate system and estimate phase | Albert | 20% | bar: WEEK 8 (11/20) S; WEEK 2 (1/15) S to WEEK 3 (1/22) S
2.6 | Iterate Algorithm to improve results | Matt | 10% | bar: WEEK 8 (11/20) S; WEEK 2 (1/15) T to WEEK 5 (2/5) S
2.7 | Develop Interface to Send Reception Angle to Master Computer | Matt | 0% | bar: WEEK 8 (11/20) S; WEEK 3 (1/22) R to WEEK 3 (1/22) S; WEEK 5 (2/5) S to WEEK 7 (2/19) S
3 | MATLAB Output | bar: WEEK 1 (10/2) S to WEEK 10 (12/4) S; WEEK 1 (12/18 S to WEEK 8 (2/26) S
3.1 | Implement Algorithm to Collate Reception Angles and Calculate Probable Location | Matt | 0% | bar: WEEK 8 (11/20) S to WEEK 9 (11/27) S; WEEK 3 (1/22) R to WEEK 3 (1/22) S; WEEK 6 (2/12) T to WEEK 7 (2/19) S
3.2 | Optimal Receiver Locations | Matt | 0% | bar: WEEK 8 (11/20) S to WEEK 9 (11/27) S; WEEK 3 (1/22) R to WEEK 5 (2/5) S
3.3 | Graphs and Performance measurements | Albert | 0% | bar: WEEK 8 (11/20) S to WEEK 9 (11/27) S; WEEK 3 (1/22) R to WEEK 3 (1/22) S; WEEK 7 (2/19) S to WEEK 8 (2/26) S
4 | Physical Testbench Construction | bar: WEEK 1 (10/2) S to WEEK 10 (12/4) S; WEEK 1 (12/18 S to WEEK 8 (2/26) S
4.1 | Purchase and Receive Antenna Elements | Matt | 100% | bar: WEEK 7 (11/13) S to WEEK 9 (11/27) S; WEEK 3 (1/22) R to WEEK 3 (1/22) S
4.3.2 | Design Mechanical Array for Antennas | Matt | 100% | bar: WEEK 8 (11/20) S; WEEK 9 (11/27) M to WEEK 10 (12/4) M; WEEK 3 (1/22) R to WEEK 3 (1/22) S
4.4 | Compare Response of Antenna Array with MATLAB Simulation | Matt | 100% | bar: WEEK 8 (11/20) S; WEEK 10 (12/4) T to WEEK 10 (12/4) S; WEEK 1 (1/8) S to WEEK 1 (1/8) T; WEEK 3 (1/22) R to WEEK 3 (1/22) S
4.4.1 | Iterate Design of Antenna Elements/Array and MATLAB Simulation | Albert | 20% | bar: WEEK 8 (11/20) S to WEEK 9 (11/27) M; WEEK 1 (1/8) W to WEEK 3 (1/22) M; WEEK 3 (1/22) R to WEEK 3 (1/22) S
4.5 | Combine SDR and Antenna Array into Functioning Prototype | Albert | 20% | bar: WEEK 8 (11/20) S; WEEK 9 (11/27) T to WEEK 9 (11/27) W; WEEK 3 (1/22) T to WEEK 3 (1/22) S
4 | Testing & Data Acquisition | bar: WEEK 1 (10/2) S to WEEK 10 (12/4) S; WEEK 1 (12/18 S to WEEK 8 (2/26) S
4.1 | Develop Testing Environment | Albert and Matt | 20% | bar: WEEK 8 (11/20) S; WEEK 3 (1/22) R to WEEK 4 (1/29) T
4.2 | Create Testbench for Outdoor Testing | Albert and Matt | 0% | bar: WEEK 8 (11/20) S; WEEK 3 (1/22) R to WEEK 4 (1/29) T; WEEK 5 (2/5) S to WEEK 7 (2/19) S
4.1.1 | Gather Data from Different Signals | Albert and Matt | 30% | bar: WEEK 8 (11/20) S; WEEK 3 (1/22) R to WEEK 3 (1/22) S; WEEK 4 (1/29) W to WEEK 8 (2/26) S
4.1.2 | Tweak Signal Processing Algorithm to Minimize Error and Test as Needed | Albert and Matt | 0% | bar: WEEK 8 (11/20) S; WEEK 3 (1/22) R to WEEK 3 (1/22) S; WEEK 4 (1/29) W to WEEK 8 (2/26) S