## Gantt Chart Template
| PROJECT TITLE | [6 empty] | COMPANY NAME
| PROJECT MANAGER | [6 empty] | DATE
[7 empty] | Fall Quarter | [69 empty] | Fall Finals | [6 empty] | Winter Break | [21 empty] | Winter Quarter
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 (10/2) | [6 empty] | WEEK 2 (10/9) | [6 empty] | WEEK 3 (10/16) | [6 empty] | WEEK 4 (1023) | [6 empty] | WEEK 5 (10/30) | [6 empty] | WEEK 6 (11/6) | [6 empty] | WEEK 7 (11/13) | [6 empty] | WEEK 8 (11/20) | [6 empty] | WEEK 9 (11/27) | [6 empty] | WEEK 10 (12/4) | [6 empty] | Haitus (12/11) | [6 empty] | WEEK 1 (12/18 | [6 empty] | WEEK 2 (12/25) | [6 empty] | WEEK 3 (1/1) | [6 empty] | WEEK 1 (1/8) | [6 empty] | WEEK 2 (1/15) | [6 empty] | WEEK 3 (1/22) | [6 empty] | WEEK 4 (1/29) | [6 empty] | WEEK 5 (2/5) | [6 empty] | WEEK 6 (2/12) | [6 empty] | WEEK 7 (2/19) | [6 empty] | WEEK 8 (2/26) | [6 empty] | WEEK 9 (3/5) | [6 empty] | WEEK 10 (3/12)
[7 empty] | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | T | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S
1 | MATLAB Simulation
1.1 | Develop General Phase Delay to Reception Angle Algorithm |  |  |  | 0 | 0% | bar: WEEK 3 (10/16) S to WEEK 4 (1023) S; WEEK 8 (11/20) S
1.2 | Model Antenna Parameters |  |  |  | 0 | 0% | bar: WEEK 4 (1023) S to WEEK 5 (10/30) M; WEEK 8 (11/20) S
1.2.1 | Antenna Electric Length |  |  |  | 0 | 0% | bar: WEEK 4 (1023) S to WEEK 4 (1023) T; WEEK 8 (11/20) S
1.2.2 | Antenna Number of Elements |  |  |  | 0 | 0% | bar: WEEK 4 (1023) W to WEEK 4 (1023) F; WEEK 8 (11/20) S
1.2.3 | Antenna Array Spacing |  |  |  | 0 | 0% | bar: WEEK 4 (1023) S to WEEK 5 (10/30) M; WEEK 8 (11/20) S
1.3 | Develop Specific Phase Delay Algorithm for Proposed Antenna Parameters |  |  |  | 0 | 0% | bar: WEEK 5 (10/30) T to WEEK 5 (10/30) R; WEEK 8 (11/20) S
1.4 | Simulate Response of Antenna Array to Signals |  |  |  | 0 | 0% | bar: WEEK 5 (10/30) F to WEEK 6 (11/6) S; WEEK 8 (11/20) S
1.4.1 | Iterate Antenna Design Using Simulation Results |  |  |  | 0 | 0% | bar: WEEK 6 (11/6) M to WEEK 6 (11/6) S; WEEK 8 (11/20) S
1.5 | Implement Frequency Division Multiplexing |  |  |  | 0 | 0% | bar: WEEK 7 (11/13) S to WEEK 8 (11/20) W; WEEK 8 (11/20) S
1.5.1 | Create Modulation Algorithm |  |  |  | 0 | 0% | bar: WEEK 7 (11/13) S to WEEK 7 (11/13) R; WEEK 8 (11/20) S
2 | LabVIEW Communication Simulation | bar: WEEK 1 (10/2) S to WEEK 10 (12/4) S; WEEK 1 (12/18 S to WEEK 8 (2/26) S
2.1 | Create Demodulation Algorithm |  |  |  | 0 | 0% | bar: WEEK 7 (11/13) F to WEEK 8 (11/20) W; WEEK 8 (11/20) S
2.2 | Port Phase Delay to Reception Angle Algorithm to LabVIEW |  |  |  | 0 | 0% | bar: WEEK 8 (11/20) R to WEEK 8 (11/20) S
2.3 | Develop Interface to Send Reception Angle to Master Computer |  |  |  | 0 | 0% | bar: WEEK 8 (11/20) S to WEEK 9 (11/27) S
3 | MATLAB Output | bar: WEEK 1 (10/2) S to WEEK 10 (12/4) S; WEEK 1 (12/18 S to WEEK 8 (2/26) S
3.1 | Implement Algorithm to Collate Reception Angles and Calculate Probable Location |  |  |  | 0 | 0% | bar: WEEK 8 (11/20) S to WEEK 9 (11/27) S
4 | Physical Testbench Construction | bar: WEEK 1 (10/2) S to WEEK 10 (12/4) S; WEEK 1 (12/18 S to WEEK 8 (2/26) S
4.1 | Purchase and Receive Antenna Elements |  |  |  | 0 | 0% | bar: WEEK 7 (11/13) S to WEEK 9 (11/27) S
4.2 | Purchase Analog Modulation components |  |  |  | 0 | 0% | bar: WEEK 7 (11/13) F to WEEK 9 (11/27) F
4.3 | Develop Pspice Model of Antenna Array with Multiplex Modulation |  |  |  | 0 | 0% | bar: WEEK 8 (11/20) R to WEEK 9 (11/27) S
4.3.1 | Implement Pspice Model onto PCB |  |  |  | 0 | 0% | bar: WEEK 8 (11/20) S; WEEK 9 (11/27) M to WEEK 10 (12/4) M
4.3.1 | Send Out PCB for Production (UCR In-House Fabrication) |  |  |  | 0 | 0% | bar: WEEK 8 (11/20) S; WEEK 9 (11/27) S to WEEK 10 (12/4) M
4.3.2 | Design Mechanical Array for Antennas |  |  |  | 0 | 0% | bar: WEEK 8 (11/20) S; WEEK 9 (11/27) M to WEEK 10 (12/4) M
4.4 | Compare Response of Antenna Array with MATLAB Simulation |  |  |  | 0 | 0% | bar: WEEK 8 (11/20) S; WEEK 10 (12/4) T to WEEK 10 (12/4) S; WEEK 1 (1/8) S to WEEK 1 (1/8) T
4.4.1 | Iterate Design of Antenna Elements/Array and MATLAB Simulation |  |  |  | 0 | 0% | bar: WEEK 8 (11/20) S to WEEK 9 (11/27) M; WEEK 1 (1/8) W to WEEK 3 (1/22) M
4.5 | Combine SDR, Multiplexer PCB, and Antenna Array into Functioning Prototype |  |  |  | 0 | 0% | bar: WEEK 8 (11/20) S; WEEK 9 (11/27) T to WEEK 9 (11/27) W; WEEK 3 (1/22) T to WEEK 3 (1/22) R
4 | Testing & Data Acquisition | bar: WEEK 1 (10/2) S to WEEK 10 (12/4) S; WEEK 1 (12/18 S to WEEK 8 (2/26) S
4.1 | Develop Testing Environment |  |  |  | 0 | 0% | bar: WEEK 8 (11/20) S; WEEK 3 (1/22) F to WEEK 4 (1/29) T
4.1.1 | Gather Data from Different Physical Signals |  |  |  | 0 | 0% | bar: WEEK 8 (11/20) S; WEEK 4 (1/29) W to WEEK 8 (2/26) S
4.1.2 | Tweak Signal Processing Algorithm to Minimize Error and Test as Needed |  |  |  | 0 | 0% | bar: WEEK 8 (11/20) S; WEEK 4 (1/29) W to WEEK 8 (2/26) S